## Notes
Notes
1 | All time is in hours
2 | Time is effort and not elapsed
3 | Assumes requirements are known
4 | Assumes requirements do not change
Legend
CHG | Time taken by CHG rota
Req | Requirements gathering
IA | Impact Assessment
TA | Technical Authority
Impl | Implementation
BAU H/O | BAU Handover - including preparation
Total | Total of the above.

## SQL Server
ID | SQL Server | Scope | CHG | Req | IA | TA | Impl | UAT | BAU H/O | Total | Comments (implementation time only considered here)
1 | SQL Server Installation (single instance) | Install MSSQL binaries for the current supported version of the DBMS (ex. SQL2008R2SP2) on one machine in compliance with build standards. Scheduling of backups and housekeeping plus inclusion in monitoring procedures. Creation of one database instance. Documentation to team standards. Raising incident with Wintel to reboot of Server | 1 | 2 | 1 | 0.5 | 15 | 7.5 | 4 | 31 | yet to Plan for Standared Installation configuration file and Best Practice guided documents
2 | Uninstalling /Decommissioning SQL Server on Standard windows Box | Uninstalling SQL server services on standard windows Box. Documentation to team standards. Raising incident with Wintel to reboot of Server | 0.5 | 1 | 1 | 0.5 | 5 | 1 | 1 | 10 | This is only applicable for Uninstalling SQL Server and it would be vary upon extra tasks i.e taking backups and scripting logins and jobs etc..
3 | SQL Server Installation on 2 Node Cluster Environment (Active-Passive) | Install MSSQL binaries for the current supported version of the DBMS (ex. SQL2008R2SP2) on one machine in compliance with build standards. Scheduling of backups and housekeeping plus inclusion in monitoring procedures. Creation of one database instance. Documentation to team standards. Raising incident with Wintel to reboot of Server | 1 | 2 | 2 | 0.5 | 20 | 5.5 | 4 | 35 | If the SQL installation is 2005 or below -16 Hours; if the SQL installation is 2008/R2 or above L12-20 Hours
4 | Un-installing SQL Services on Cluster Environment | Un-installing SQL server services on Cluster windows Environment. Documentation to team standards. Raising incident with Wintel to reboot of Server | 1 | 2 | 2 | 0.5 | 8 | 1 | 1 | 15.5 | For SQL server 2005 or below versions -6 Hours; for SQL server 2008 and above versions -8 Hours;
5 | Install Additional Services on exiting SQL instance | Install MSSQL other Services under existing SQL instance. Documentation to team standards. | 0.5 | 1 | 1 | 0.5 | 3 | 1 | 1 | 8
6 | Install Additional Services on exiting SQL instance with cluster aware | Install MSSQL other Services under existing SQL instance. Documentation to team standards. | 0.5 | 1 | 2 | 0.5 | 6 | 1 | 1 | 12 | For SQL server 2005 or below versions - 5 Hours; for SQL server 2008 and above versions -6 Hours;
7 | Adding new node to the existing cluster environment | install SQL installation media on new node & coordinating with Wintel , apps & other teams to check the server status in cluster Aware | 0.5 | 1 | 1 | 0.5 | 5 | 1 | 1 | 10 | 5 hours is applicable for only one node and if it 2 nodes it would be 8 Hours
8 | DBMS Patching | Applying a hot fix to an existing DBMS installation. Raising incident with Wintel to reboot of Server and notifying business about Server outage timings (including monitoring team) | 1 | 1 | 1 | 0.5 | 5 | 1 | 1 | 10.5 | if any case Msi or MSP files are missing that case it would be -10 hours
9 | DBMS Patching on Cluster aware nodes (2 node) | Applying a hot fix to an existing DBMS instance on Cluster. Raising incident with Wintel to reboot of Server and notifying business about Server outage timings (including monitoring team) | 1 | 2 | 1 | 0.5 | 7 | 1.5 | 1 | 14 | if any case Msi or MSP files are missing that case it would be -12 hours for impl
10 | DBMS Upgrade/Migration | Upgrade to a new major version of the DBMS, e.g. SQL2005 to SQL2008R2.plus inclusion in monitoring procedures. Documentation to team standards. Raising incident with Wintel to reboot of Server and notifying business about Server outage timings (including monitoring team) | 1 | 2 | 1 | 0.5 | 15 | 4 | 2 | 25.5 | This is applicable for only inplace upgrades , if the requirement is for side by side upgrade then it would be 20 hours
11 | Database Movement (migration) | Moving Database from SQL Server 2000 to 2005/2008/R2/2012 etc ..environment | 1 | 2 | 1 | 0.5 | 4 | 1 | 1 | 10.5 | if the database movement is from 7.0 or below versions then it would be 6 hours
12 | Additional SQL Server Instance installation | Creation of a additional server instance on a machine which already has binaries installed. Scheduling of backups and housekeeping plus inclusion of the new database into monitoring procedures. Raising incident with Wintel to reboot of Server and notifying business about Server outage timings (including monitoring team) | 1 | 2 | 2 | 0.5 | 7.5 | 2 | 2 | 17
13 | Additional SQL Server Instance installation on cluster Aware (Active-Active) | Creation of a additional server instance on a machine which already has binaries installed. Scheduling of backups and housekeeping plus inclusion of the new database into monitoring procedures. Documentation to team standards. Raising incident with Wintel to reboot of Server and notifying business about Server outage timings (including monitoring team) | 1 | 2 | 2 | 0.5 | 10 | 3.5 | 2 | 21
14 | Database Creation & Dropping & Truncating Tables | Creation/Dropping /Truncating database (tables) in an existing server instance. | 0.5 | 0.5 | 1 | 0.5 | 2 | 1 | 1 | 6.5
15 | Standby Database Creation (Mirroring & logshipping) | The creation of a standby database and the setup of data replication procedures (i.e. user-scripted log-shipping, mirroring, publisher/subscriber replication). | 1 | 2 | 2 | 0.5 | 4 | 2 | 1 | 12.5 | Applicable for 1 Database
16 | Transition to BAU support (Taking Server into BAU Scope) | Knowledge transfer with previous support team. Acquisition of passwords and connectivity to the existing database server. Documentation of the configuration to team standards. Cascading KT to the remainder of the team. | 1 | 2 | 1.5 | 0.5 | 4 | 1 | 4 | 14 | Applicable for 1 Server
17 | Ad-hoc backup | Running the standard backup script at a time outside of the regular backup schedule. | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0.5 | 0 | 4.5 | Applicable up to 5 databases.
18 | Ad-hoc restore (Prod < - >Test ) | Restoring a backup from the production system into a non-production system. The source and destination instance must already exist. | 0.5 | 1 | 1 | 0.5 | 2 | 1 | 1 | 7 | Applicable for 1 Database.
19 | OS Patching Support | Graceful shutdown of DBMS instance before the OS patching. Startup of the DBMS instance and running checks to verify the DBMS layer is working. | 0.5 | 1 | 1 | 0.5 | 1 | 1 | 0 | 5 | Applicable for 1 Server
20 | OS Patching Support with cluster aware | Graceful failover and failback of 2 node cluster before the OS patching. Startup of the DBMS instance and running checks to verify the DBMS layer is working. | 1 | 2 | 1 | 0.5 | 2 | 1 | 0 | 7.5 | Applicable for 2 node cluster
21 | Data fix (script execution) | Run a standard script provided by Application Support against the production database. The script is well known and can be run at any time. | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0 | 4
22 | Minor configuration changes on Database level | Any one of the following where the value is already known:- * change in backup or housekeeping schedule * Database properties * internal DBMS account maintenance(login creation) | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0 | 4
23 | Minor configuration changes with Graceful restart of SQL services | Any one of the following where the value is already known:- * startup parameter change * changes in SQL Server security / Memory / registry | 1 | 1 | 0.5 | 0.5 | 2.5 | 1 | 0 | 6.5
Note on H2: Author: between 11 to 15 , Based on request